AnalytiProject

--------------

Project Planner in AnalytiCalc

------- ------- -- -----------

Motivation

----------

The idea here is to allow you to express networks of activities

here, one activity to a line (row) and say what the dependencies of

each on others are. You enter the project start date, the name of

each sub-activity, what others it depends on, the duration of each,

and the amount of "resource" used by each. You get back the start and

end dates for each, a plot on screen of resource usage vs. time (with

fixed 24 bins, each 1/24 of the total duration), and information on

which activities form the "critical path". The critical path is the

set of activities that make your project end when it does rather than

earlier. If you alter the duration of one of the activities on the

critical path, it will usually shorten the project. However, since

other activities may then become the critical ones, this cannot be

always guaranteed.

The plot of resource use vs. time is handy in that it will

let you tell if you're going to be overcommitted. If for example

your "resource" is people and it shows 10 used where your shop

has only 6, you know things are in trouble. You'll need to add some

dependencies to the network to express the notion that some later

activities have to depend on more earlier ones being done then,

due to the availability of people rather than the logic of the

rest of the project.

Detail

------

The project planner consists of the saved spreadsheet file PPLN.PCC

and the two page displayers, PPLNS1.CMD and PPLNS2.CMD. An optional

component is the file APPLN.CMD.

If you use the APPLN.CMD file, you need only fire up AnalytiCalc

and type @APPLN.CMD with the other files in your default directory.

The command file will load the planner template and set command Q

to run the critical path command file (PPLNS1.CMD) and command Y

to run the screen display of times (PPLNS2.CMD). This will save

keystrokes. (Cells B0, J0, N0, Q0, T0, U0, and Y0 can be filled in

with text commands to be executed by commands B, J, N, Q, T, U, or

Y respectively if you wish to shorten some extra commands.)

To use the planner, load PPLN.PCC with a GP command (or key

1 on the auxiliary keypad, or APPLN.CMD). Then for the first activities,

modify rows 3 through 6 as needed. You will want to modify column A, the

activity titles, column B, the preconditions, and column D, the

duration of the activity required. Also modify column J if desired

by entering the amount of some resource (1. to whatever maximum

you like) needed for the activity you're describing.

Also enter the project starting date as YY/MM/DD in cell

F2 where it is labelled.

To add more activities, use the AR command. Go to the

row you want in the range 4 to 6 and add rows. Note that the

old rows' contents are not altered.

A sample command sequence to add 8 more activity rows

would be:

L A4		go to row 4

AR 1R		Add one row for starters

AR 2R		Add two more rows

AR 4R		Add four more

AR 2R		Add the last two.

This sequence is used so that the formulas in columns other

than the ones you modify are duplicated; this is needed for

correct operation.

Once you finish adding as many rows as desired, modify

columns A, B, D, and J as appropriate. The order you enter activities

in is not important. Then recalculate a number of times to get

the dates correct. The R command recalculates.

To obtain a display sorted by start date the command

DSCA 6

could be used (possibly aftera DB command to reset the display bounds

to area actually used). The VAX display can be set to up to 200

rows long for purposes of a W command to write the sorted

display to the printer or a file. Other columns may be sorted if

desired; in the normal format, column 6 of the display is physical

column F and column 7 is column G, the end dates.

To see the critical path, use the command @PPLNS1.CMD to

compute the critical path. Column I will have 1 in each activity

that lies on the critical path at the end. (If it doesn't seem to

come all the way back to the project start, use the commands:

L L3

DF P#%DD:D#%DH [*]

R

R

R

R

R

DF P#%DD:D#%DH [A]

to extend the recalculation to get to the start.

To see a plot of resource usage vs. time (with 24 bins of

time), use the command file @PPLNS2.CMD to set up.

The critical path is shown in the page with the plots, so

use PPLNS1.CMD first to calculate the critical path. The computation

is not done initially so you can enter your project more quickly,

and because a few global values must be computed from the data

which are "forward references" in the spreadsheet. If the equations

that compute and graph the project activities were initially

enabled, they would blow up the first time through. The use of the

command files to control execution obviates the problem and allows

the system to work.

Other files beginning with PPLN8 are for an 80-column only

version of the planner. They show less, but leave your terminal

in 80 column mode, making it easier to read.

Generalizations

It is fairly simple to make the durations be functions of

a global accumulator (so that one would enter a duration of 5.*G

for example rather than just 5.) and to have that accumulator's

initial value be 1.0. If this is done, the goal-seeking capacity

of AnalytiCalc can be used to vary G to find that set of durations

such that the project is done by a given date. More complex schemes

using several accumulators with boundary conditions could be

devised also.

Hooks to other saved plans could be added by placing

the links anywhere desired and using their addresses in the

lists of dependencies in column B. Normally one enters addresses

like A4, A5, A5:A11,A15 or similar forms in column B. However,

so long as the values referred to are Julian dates, they can be

obtained anywhere. Simply place an *XV filename,cell somewhere

in the current sheet and include the address of the cell with the

*XV in it in your column B and you have a link to other plans.

If the other plans are saved versions of PPLN.PCC expanded,

cell Am (m being a row number in the saved sheet) would contain a

Julian date value in the needed form, provided the sheet was saved

with values as well as formulas (i.e., saved with PPX, not PPF.)