IPM.PAS & IPM.COM - Version 1.07 - November, 1984

(c) 1984 by Edward V. Dong, All Rights Reserved.

Programmed by:

Edward V.  Dong

12205 Alexandria Place

Chino, CA 91710

1.0   GENERAL

IPM.COM  is  a  Critical  Path  Method  Project  Scheduler.   The

Critical  Path  Method  is  a  methodology  for  determining  the

critical  tasks  that,  if  not  accomplished  by a certain time,

contribute  directly  to  the  delay  of  the whole project.  You

should refer to various books on the subject.

1.1  RIGHT  TO  USE THIS SOFTWARE.  The software, IPM.COM, may be

used as is, by anyone  for  private  purposes  only.   Commercial

users  should contact the address above for the right to use this

software.  No claim is made for the veracity  of  this  software,

and  no warranty, guarantee or other bond is expressed or implied

about the use of this software.  No user may sell  this  software

in  any  form,  other than for the cost of materials and mailing,

without the express, written consent of Edward V.  Dong.

This software and documentation is copyright (c) 1984  by  Edward

V. Dong, all rights reserved.

You are encouraged to share and  copy  this  software  otherwise.

Contributions  ($10  for example) and comments should be directed

to the above address.

1.2  REQUIREMENTS.   IPM will run in a minimum of 128K, under DOS

1.1, 2.0, and 2.1, and should run  under  DOS  3.X.   Written  in

Turbo  Pascal 1.0, IPM requires an IBM PC, XT, PC-3270, or AT, or

a close PC compatible that  supports  IBM  BIOS  ROM  calls.   It

should run with or without a color graphics board.

The  maximum  number  of  activities  that it will handle, is 100

(actually 99), determined by the constant MaxValue in the  source

code IPM.PAS.

Various calculations and plots can be printed to an  EPSON  or  a

compatible  printer,  by first outputing them to a disk file, and

then  printing  those  files.   Basic  calculation  data  can  be

exported as a .PRN file to Lotus 1-2-3.

1.3  THEORY  OF  OPERATIONS.   Briefy,  the  CPM theory is that a

project is composed of tasks or activities that are arranged in a

pattern  or  network,  where  some  tasks  may  be  performed  in

parallel.

If two tasks are being performed in parallel, then the  one  that

takes  longer  to  do,  is  termed "critical".  It is "critical",

because a delay in that task directly contributes to the delay of

the whole project.  A delay in the other task -- as long as it is

completed before the longer task -- does not.  The difference  in

completion time is called "slack".

The idea in project scheduling and management is to arrange these

tasks, and to monitor them,  so  that  the  time  for  the  whole

project is kept as short as possible, or the resources needed for

the project is "levelled".  That is, you  don't  want  to  spend,

say, 6 men for 2 weeks on one part of the project, and only use 1

man for the remaining 12 weeks of  the  project;   rather,  as  a

manager,  you want to spread your manpower (or other resource) as

evenly as possible, because it becomes easier to manage.

1.4  BACKGROUND.   IPM was originally coded because of, first, an

admiration  for  the  Harvard  Project  Scheduler,  and,  second,

certain  deficiencies  in  the  HPM.   IPM indeed stands for "Ivy

League Project Manager".  While most features found  in  HPM  are

incorporated  into  IPM,  IPM  however  does  not have a calendar

function nor a project-tracking function.   These  may  be  added

later.

IPM  is  an  evolutionary  outgrowth  of  an  earlier  scheduling

program, written  by  E.   Dong,  called  CPM.COM.   CPM.COM  was

originally  coded  18  Sept  83  by  E.  Dong, based on the BASIC

version, 'Hard Hat Management:  Two On-Site  Tools',  by  Richard

Parry,  INTERFACE  AGE,  February, 1981.  It was first translated

into CIC86 'C', and then retranslated into Turbo Pascal, with the

last update on 24-Mar-84.

The  current  program, IPM.COM, was adapted from PRACTICAL PASCAL

PROGRAMS, Osborne/McGraw-Hill, by  Greg  Davidson,  (c)  1982  by

McGraw-Hill,  Inc.   However,  this  was extensively modified, as

this book did not address the creation of GANTT or PERT charts.

The algorithm for IPM's GANTT charts is based on that created for

CPM.COM,  while  the  algorithm  for  IPM's PERT charts was newly

created (in three days of intensive development).  A  semi-screen

editor was also created for IPM.COM.

2.0   STARTING IPM

Starting IPM is, after it has  been  copied  to  the  appropriate

disk,  to  type  IPM.   When  it  pops  up on the screen, it will

display a copyright logo, a brief text indicating  the  reference

to  Greg Davidson's book, and a brief description of how to enter

commands.

IPM is arranged so that line 25 (and occasionally, also line  24)

shows the current available commands.  You execute these commands

by typing the first letter (which should be high-lighted) and  no

carriage return.

Initially,  the  only  options  you have at startup are:  F(ile),

Q(uit), and H(elp).  QUIT returns you to DOS;  in some cases,  it

will  return  you  to  a  previous  command  menu  instead.  HELP

generates a quick summary of the basic commands  only.   FILE  is

the  command  that  you must enter first, in order to do anything

with IPM.

FILE allows you to specify the method of data  entry.   That  is,

you  can enter project data interactively at the console, or from

a file.  If you're using IPM for the first time, generally  there

would  be  no  files  for  IPM  to  use,  so  you must enter data

initially at the console directly.  FILE will prompt you for your

option.

You  should  have  a  minimum of four tasks to use IPM;  anything

else, would be a waste of time with IPM.

Entering  necessary  input  data  is as follows.  First, IPM will

prompt:

Input from Console? (Y/N)

Either an upper- or lower-case "y" or "n" may be entered.  If

you  enter  "N",  then IPM will ask for the name of the file.

This file must be in  the  current  subdirectory,  if  you're

using DOS 2.0 or higher;  IPM isn't smart enough (right now!)

to access across subdirectories.

If you answer "Y", then IPM will ask:

Enter Project Title/Description:

You can enter a  60-character  description  of  the  project.

This  title  or  description  will  appear  at the top of the

screen to let you know what project IPM is working on.

Then, IPM will prompt for the number of tasks  that  comprise

this project:

Enter Number of Tasks on this network:

As  was  said before, you should have a minimum of four tasks

to use IPM;  anything else, would be a  waste  of  time  with

IPM.   Then the screen will clear, and display something like

the following:

PROJECT: Sample -- Editing

----------------------------------------------------------------

Task Start  End

Node Node  Duration  Cost Name/Description

1    0    0    0.00   0.00    Task01

2    0    0    0.00   0.00    Task02

3    0    0    0.00   0.00    Task03

4    0    0    0.00   0.00    Task04

where "Sample" here is  the  project  title/description  that

you've entered.  IPM tells you that you are in editing  mode,

and  will have supplied a generic task name for the number of

tasks you've indicated, such as "Task01".

At this point, you will see a double command line (lines 24 &

25).  You can use the command options (remember,  enter  only

the  first or high-lighted letter of the option) to alter and

enter the task data.

You should do the following:

o IPM  assumes  that the first node is numbered "1", and that

the last possible node is a number less than  or  equal  to

the  total  number  of  tasks.  Therefore, you must specify

"Start" and "End" nodes for each task.

o "Duration" refers to the expected length of time  that  the

task  should take.  No units are used, so you can use days,

hours, minutes, or even seconds if you want.  However,  you

should use the SAME unit of time (days, weeks, or whatever)

for all entries.

To edit a line in the display, you must first enter  the  Taskno.

When  you  have done so, the line in the display will high-light.

Then you can change Duration, Task title, Task description,  etc.

The Task Title, however, is limited to 8 characters only.

You  can  insert either a new Task or a new Node.  If you enter a

new Node, you MUST specify a current Task number to go with  that

new Node.

To  finish  the editing, enter the command Q(uit).  IPM will then

prompt you if you want to save it to disk, and if so,  what  name

should it give the file.  If the file exists, IPM will ask you if

you want to overwrite (reuse) the file.

3.0  OPERATING IPM

Once you have entered the task data, you then have the following

options:

CALCSHEET:  Calculate critical path, total project  duration,

and cost.  You MUST run this option before doing...

GANTT:  Build a GANTT chart on the console.  If the CalcSheet

option was not exercised, then you will be prompted to do so.

The GANTT chart is normalized, that  is,  the  time  line  is

scaled to fit the CRT display.  The scaling is indicated.

PLOT:   Build  a PERT network chart of the project.  Here you

will see the tasks going from Node to Node, in  the  sequence

that  you've  entered.  Since many managers and professionals

need to see a PERT chart first, this option has the suboption

of  Editing  as  well.   Then  you  will  go through the same

editing as before, except that the Edit screen appears in the

lower  half  of  the  CRT display, so you can see the current

PERT network.  When you have  finished  editing,  the  screen

will flicker once or twice, and then paint the new PERT chart

that is the result of your editing.

EDIT:  Edit tasks, as described above.

FILE:  Once you have entered data (either from the console or

from  disk), the next time you request F(ile), it will ask if

you want to do a N(ew project) or to O(utput to  file).   See

Section 4.0 below.

QUIT:   Return  to  DOS.  IPM will NOT ask you if you want to

save the current file, so be warned.

4.0  ADVANCED IPM FILE OPTIONS

After you have first entered data via F(ile), the next time (and

thereafter) you enable F(ile), it will ask you if you want to do

a N(ew project), O(utput to file), or Q(uit to main menu).

N(ew project):  This is the same as if you were entering data

for the first time to IPM.

O(utput  to File):  When you select this option, you will see

a new command menu line of C(alcSheet), G(antt), P(lot),  and

L(otus).  For C, G, and P, you will first be prompted for the

filename to send the output to;  this can be "LPT1:" for  the

printer, but this is NOT encouraged.  (Save to file first, so

you can use your text editor to modify the file for  whatever

purpose.)

L(otus):   This  option  outputs  the results of calculations

into a file, which should be called  with  extension  ".PRN".

Then  you  can  use Lotus 1-2-3 to IMPORT the file (using the

NUMBERS option in Lotus), and  thus  generate  a  .WKS  file.

Once  you've  done  that,  you  can now use the full power of

Lotus on it.

Q(uit):  Returns you to the main menu display.

The  file/printer  output  of the G(antt) and P(lot) options will

differ from the CRT display.  The reason for this, is  to  enable

the  use of any ASCII-supported printer;  except for IBM printers

and EPSON FX printers (with the  appropriate  fonts  downloaded),

the  IBM  display characters above ASCII code 128 decimal are not

uniformly supported.

5.0  USEFUL TIPS

IPM uses a normalized time scale.  That is, IPM does not  attempt

to   allocate  tasks  to  a  calendar  schedule,  although  this,

obviously,  is  a  prime  objective.   Thus,   you   should   use

"normalized"  time  units,  such as hours, days, or minutes;  you

should use minutes, for example, if you are using  this  to  plan

activities  that will span an eight-hour day or less;  hours, for

projects under a week;  and days for longer-lived projects.

#########################