.MT0

.MB0

PPPPPP     CCCCCC   PPPPPP    M     M

P     P   C         P     P   MM   MM

P     P   C         P     P   M M M M

P     P   C         P     P   M  M  M

PPPPPP    C         PPPPPP    M  M  M

P         C         P         M     M

P         C         P         M     M

P         C         P         M     M

P          CCCCCC   P         M     M

PERSONAL COMPUTER PROJECT MANAGEMENT

PREPARED BY:

Len Shepard

444 North 3rd Street, Suite 201

Sacramento, CA  95814

(916) 446-1615

November 21, 1984

TABLE OF CONTENTS

Page

I.  INTRODUCTION

A.  PREPARATION

1.  The Node Network                                  1

2.  The Input Worksheet                               1

B.  ENTERING THE BASE FILE                               2

C.  SYSTEM GENERATED FILES                               2

D.  CHANGING THE INPUT FILE                              2

II.  SAMPLE SESSION RUNNING PCPM                              3

A.  Creation of Sample File                              4

1 - INFORMATION                                     4

2 - ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE         5

3 - ENTER/CHANGE INPUT FILE                         7

Change Project Title                            7

Input/Add Activities                            9

Delete Activities                              10

Change Activity Data                           12

Change Time Period Units                       14

Change Start Date                              15

Inspect Input File                             16

Check Node Connections                         18

Sort and File Input                            19

Filing Changes                                 20

4 - CREATE/CHANGE HOLIDAYS                         22

5 - PERFORM CRITICAL PATH ANALYSIS                 24

6 - PERFORM CASH FLOW ANALYSIS                     25

7 - PRODUCE BAR CHARTS                             26

8 - SORT OUTPUT                                    28

9 - EXTRACT OUTPUT BY SUBCONTRACTOR                30

Page

____

10 - CHECK NODE NUMBERS                             31

11 - PRECEDENCE OR SUCCEEDENCE DISPLAY              32

12 - CONVERT WORKING DAYS TO PROJECT DAYS           33

13 - GENERATE CURRENT COST REPORT                   34

14 - CHANGE ALL NODE NUMBERS                        35

15 - CONSOLIDATE UPDATE FILES TO INPUT FILES        36

EXITING PCPM                                        37

III.  SYSTEM ERRORS                                           38

IV.  OUTPUT

A.  Primary                                             39

B.  Cash Flow Analysis                                  39

C.  Barchart                                            39

D.  Current Cost Report                                 39

E.  Preceeder or Succeeder Display                      39

V.  APPENDIX

A.  Sample Input Form                                   40

PC PROJECT MANAGEMENT               1                     USER'S MANUAL

I.  INTRODUCTION

PCPM is  a  system of interactive programs for project management using

the critical path  method.   The  system  is  designed  to  handle  all

necessary functions  internally or allow the more sophisticated user to

build and modify files on his/her own by making use of  system  editing

software.  PCPM is menu-driven, that is, a menu of available options is

displayed to  the  terminal  for the user to choose the desired option.

When that particular function  has  been  completed,  PCPM  will  again

display the menu.

A.  PREPARATION

1.  The_Node_Network

To use PCPM the user must first have constructed a node network

representation of  the  project.   Each  activity  must  have a

description of up to 30 characters, a duration (time), and node

numbers.

The node network numbering must  be  performed  in  a  specific

fashion.  Each  node  is  assigned  an integer number from 1 to

1000 and nodes are numbered in ascending order with  the  first

node having  the  lowest  number  and  the last node having the

highest number.  The "from" node for each activity must be less

than (and not equal to) the "to" node for that activity.   Note

that not  all  numbers  between the start and finish have to be

used;  in fact, spacing  should  be  maintained  to  allow  for

future schedule changes.

2.  The_Input_Worksheet

Before input  at  the  terminal  is attempted, it is helpful to

make an input worksheet.  Enter the information from  the  node

network.  (See samples in the appendix).

Optional entries  for each activity are the report finish date,

percent complete, subcontractor name/code or other comment, and

activity cost.

Any report finish date entered must be "legal".  To be legal  a

date can  not fall on a weekend or holiday when working days is

the unit of time being used.  Also, a legal  date  can  not  be

prior to the start date of the project.

PCPM may  be run using any unit of time the user specifies.  It

is, however, up to the user to maintain consistency  of  input.

Examples of possibilites are:

Working days (does include weekends but not holidays).

Calendar days (does not include holidays).

PC PROJECT MANAGEMENT               2                     USER'S MANUAL

Weeks (activity duration must be converted by the

user - e.g., 10 days duration should be entered as 2).

B.  ENTERING_THE_BASE_FILE

Using PCPM,  a  sample  input file such as that on pages 4-5 can be

created.  Other functions, including creation of  a  holiday  file,

critical path  and  cash flow analyses, and sorting output are also

performed by using PCPM.

The user is guided interactively through each option of  the  menu.

After each option is complete, the system returns to the menu.

C.  SYSTEM_GENERATED_FILES

Accessory files  to  the input file are created by the system based

upon the input file.  It is, therefore, important that this file be

accurately entered.  In general, the existence  of  system  created

files can  be  ignored  by  the  user.  They are merely cogs in the

machinery that allows PCPM to run.  The  following  information  is

included to satisfy the more curious users.

As options of the Main  Menu  are  performed,  the  system  creates

accessory files.  These accessory files are described with the base

file  name  and  a  three  letter  extension.   For  example,  when

utilizing OPTION 4 - CREATE/CHANGE  HOLIDAYS,  the  system  creates

(automatically) a file denoted by BASEFILENAME.HOL.

Here are  some  of the system created files for example file "LLP":

LLP.CFA   - output file for cash flow analysis

LLP.CPM   - input file for option 5 (main file)

LLP.CST   - output file for current cost report

LLP.DAY   - file of working vs. project days from Option 12

LLP.HOL   - file of holidays created by Option 3

LLP.LGS   - file of data for sorts used by Options 6,7,8, & 9

LLP.PRE   - output file containing predecessor printout

LLP.SRT   - sorted output file created by option 8

LLP.SUC   - output file containing successor printout

LLP.UPD   - updated input file created by Option 5

D.  CHANGING_THE_INPUT_FILE

Changing the  input  file  is  easily   done   by   changing   node

connections, durations,  and/or  adding  report finish dates.  Once

the modifications to the input file are made, rerun Option 5.   The

system will quickly calculate the new durations, critical path, and

completion times.

PC PROJECT MANAGEMENT               3                     USER'S MANUAL

II.  SAMPLE SESSION RUNNING PCPM

The following is a sample of what the completed input file, called LLP,

looks like.

P&L CONSTRUCTION PROJECT

1,MOBILIZATION,500,510,2,1,0,0,0,1,0

2,GRADE & CLEAR SITE,510,520,5,4,0,0,0,2,0

3,REBAR PIERS,520,530,5,9,0,0,0,3,0

4,POUR PIERS,530,550,5,0,0,0,0,4,0

5,EXCAVATE FOUNDATIONS,550,560,8,8,0,0,0,5,0

6,REBAR FOUNDATIONS,560,570,5,5,0,0,0,6,0

7,ANCHOR BOLTS,570,580,2,2,0,0,0,7,0

8,POUR & CURE FOUNDATIONS,580,585,5,5,0,0,0,8,0

9,STRUCTURAL STEEL,585,587,10,10,0,0,0,9,0

10,DECK FILL CONC.,590,600,15,15,0,0,0,10,0

11,WELD STRUCTURAL,587,595,20,20,0,0,0,11,0

12,FIRE PROOFING,620,625,5,5,0,0,0,12,0

13,PRECAST PANELS,625,650,20,20,0,0,0,13,0

14,P.M. FRAMES,600,790,2,2,0,0,0,14,0

15,WALL FRAMING,600,790,20,20,0,0,0,15,0

16,SHEET METAL DUCTWORK,600,955,40,40,0,0,0,16,0

17,ELEC. RGH. IN,620,640,10,10,0,0,0,17,0

18,MAIN ELEC PANEL,640,790,10,10,0,0,0,18,0

19,PLUMING RGH IN,620,630,5,5,0,0,0,19,0

20,POUR S.O.G.,630,790,8,8,0,0,0,20,0

21,STAIRCASES,585,590,25,25,0,0,0,21,0

22,PLUMB. TOP OUT,630,890,10,10,0,0,0,22,0

23,ELEC. PULL WIRE & POWER,640,760,10,10,0,0,0,23,0

24,ELEC. FIXTURES/SWITCHES/PLUGS,760,960,5,5,0,0,0,24,0

25,STAIR FILL,597,710,10,10,0,0,0,25,0

26,INSULATION,790,800,2,2,0,0,0,1,0

27,DRYWALL,800,810,10,10,0,0,0,27,0

28,CERAMIC TILE,810,850,20,20,0,0,0,28,0

29,PAINT INTERIOR,810,860,10,10,0,0,0,29,0

30,DUMMY,860,870,0,0,0,0,0,30,0

31,STAIN DOORS,870,920,5,5,0,0,0,31,0

32,FINISH HARDWARE,920,960,5,5,0,0,0,32,0

33,METAL SIDING,650,890,2,2,0,0,0,33,0

34,ACCESS LADDER,950,960,1,1,0,0,0,34,0

35,REGISTERS & GRILLS,955,957,5,5,0,0,0,35,0

36,BALANCE H.V.A.C.,957,960,2,2,0,0,0,36,0

37,TOILET FIXTURES,850,910,5,5,0,0,0,37,0

38,TOILET PARTITIONS,910,940,2,2,0,0,0,38,0

39,PAINT STAIRS,710,960,3,3,0,0,0,39,0

40,CURBS & SIDEWALKS,650,960,5,5,0,0,0,40,0

41,FINAL CLEAN UP,960,970,2,2,0,0,0,41,0

42,DUMMY,600,620,0,0,0,0,0,42,0

43,ROOF HATCH,890,950,1,1,0,0,0,43,0

44,DUMMY,587,590,10,10,0,0,0,44,0

45,METAL DECK WELD,587,597,25,25,0,0,0,45,0

46,DUMMY,810,955,0,0,0,0,0,46,0

47,DUMMY,595,597,5,5,0,0,0,47,0

48,TOILET ACCESSORIES 0,940,960,2,2,0,0,0,48,0

PC PROJECT MANAGEMENT               4                     USER'S MANUAL

A.  CREATION_OF_THE_INPUT_FILE_"LLP"

The following  is  an  actual  session  which you can duplicate on your

computer.  User responses are underlined.  Remember to use  UPPER  CASE

responses only.  Comments and explanations are indicated by "/*".

OPTION_1_-_INFORMATION

A> PCPM

Copyright information  shows  on  the  screen.   Press the space bar to

continue running PCPM.

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER  _1_

INFORMATION ON THE PCPM SYSTEM

PCPM is a menu driven Critical Path  Method.   Several  utilities  make

this system  a valuable tool for project management.  Input can be done

interactively in PCPM or be edited outside the PCPM system using  EDLIN

(IBM) or EDCOL (P&L).

Using PCPM, you are guided interactively through each menu option.   As

each function is completed the screen returns to the main menu.

Information and  messages  from  the  system  are  displayed  in   CAPS

surrounded by  "****".   User  responses  should  be made in UPPER CASE

LETTERS only.  Answers to prompts are  provided  in  paranthesis,  like

(Y/N).  The first answer (Y) is the default (<CR> key) answer.

For detailed information refer to the PCPM USERS  MANUAL.   If  further

assistance is needed, call (916) 446-1613.

Hit ENTER when you are ready to return to the main menu.  <CR>

PC PROJECT MANAGEMENT               5                     USER'S MANUAL

OPTION_2_-_ENTER/CHANGE_SUBCONTRACTOR/COMMENT_FILE

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER 2

Enter the name of the input file [.CPM] ? LLP

Project: P&L CONSTRUCTION                          File: LLP.CPM

Time Period Units: WORKING DAYS   Sub. Codes: 48   Start Date: 070183

SUBCONTRACTOR/COMMENT CODES

Add, Change, Delete            1 WILSON    17 MACFORD    33 KRENCHIK

or Quit (A/C/D/Q) ? D          2 JONES     18 MCCALL     34 LEACH

3 MILLER    19 TRAMMEL    35 FREEHAN

Enter Code number              4 ARCHS     20 WHITE      36 TRESH

or 0 to exit ? 24              5 LEMON     21 CABELL     37 WERST

6 BUGMAN    22 BROOK      38 LOLICH

Enter Code number              7 SHECK     23 GIBSON     39 BUNNING

or 0 to exit ? 0               8 WILLIS    24 GENET      40 MCLAIN

9 MEAD      25 KALINE     41 NORTHRUP

10 KNOUS     26 WILSON     42 STANLEY

11 HOM       27 PARR       43 OYLER

12 HEDIN     28 MORRIS     44 CASH

13 ROBER     29 BEREN      45 WOCKFUSS

14 MAST      30 WILCOX     46 GRUBB

15 JONEY     31 LOPEZ      47 COBB

16 FURRER    32 BAIR       48 GRENBERG

PC PROJECT MANAGEMENT               6                     USER'S MANUAL

Project: P&L CONSTRUCTION                          File: LLP.CPM

Time Period Units: WORKING DAYS   Sub. Codes: 48   Start Date: 070183

SUBCONTRACTOR/COMMENT CODES

Add, Change, Delete            1 WILSON    17 MACFORD    33 KRENCHIK

or Quit (A/C/D/Q) ? C          2 JONES     18 MCCALL     34 LEACH

3 MILLER    19 TRAMMEL    35 FREEHAN

Enter Code number              4 ARCHS     20 WHITE      36 TRESH

or 0 to exit ? 8               5 LEMON     21 CABELL     37 WERST

6 BUGMAN    22 BROOK      38 LOLICH

Enter New Name/Comment         7 SHECK     23 GIBSON     39 BUNNING

WILLS                          8 WILLIS    24            40 MCLAIN

9 MEAD      25 KALINE     41 NORTHRUP

Enter Code number             10 KNOUS     26 WILSON     42 STANLEY

or 0 to exit ? 0              11 HOM       27 PARR       43 OYLER

12 HEDIN     28 MORRIS     44 CASH

13 ROBER     29 BEREN      45 WOCKFUSS

14 MAST      30 WILCOX     46 GRUBB

15 JONEY     31 LOPEZ      47 COBB

16 FURRER    32 BAIR       48 GRENBERG

Project: P&L CONSTRUCTION                          File: LLP.CPM

Time Period Units: WORKING DAYS   Sub. Codes: 48   Start Date: 070183

SUBCONTRACTOR/COMMENT CODES

Add, Change, Delete            1 WILSON    17 MACFORD    33 KRENCHIK

or Quit (A/C/D/Q) ? Q          2 JONES     18 MCCALL     34 LEACH

3 MILLER    19 TRAMMEL    35 FREEHAN

File Changes or Quit           4 ARCHS     20 WHITE      36 TRESH

(F/Q) F                        5 LEMON     21 CABELL     37 WERST

6 BUGMAN    22 BROOK      38 LOLICH

7 SHECK     23 GIBSON     39 BUNNING

8 WILLS     24            40 MCLAIN

9 MEAD      25 KALINE     41 NORTHRUP

10 KNOUS     26 WILSON     42 STANLEY

11 HOM       27 PARR       43 OYLER

12 HEDIN     28 MORRIS     44 CASH

13 ROBER     29 BEREN      45 WOCKFUSS

14 MAST      30 WILCOX     46 GRUBB

15 JONEY     31 LOPEZ      47 COBB

16 FURRER    32 BAIR       48 GRENBERG

PC PROJECT MANAGEMENT               7                     USER'S MANUAL

OPTION_3_-_ENTER/CHANGE_INPUT

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER  3

Enter the name of the input file [.CPM] ?  LLP

10  20  30  40  **** INPUT FILE READ ****

INPUT_OPTION_1_-_CHANGE_TITLE

Project: P&L CONSTRUCTION                          File: LLP.CPM

Time Period Units: WORKING DAYS   Activities: 48   Start Date: 070183

INPUT MODIFICATION MENU

EXIT MODIFICATION                        - 0

CHANGE TITLE                             - 1

INPUT/ADD ACTIVITES                      - 2

DELETE ACTIVITIES                        - 3

CHANGE ACTIVITY DATA                     - 4

CHANGE TIME PERIOD UNITS                 - 5

CHANGE START DATE                        - 6

INSPECT INPUT                            - 7

CHECK NODE CONNECTIONS                   - 8

SORT AND FILE INPUT                      - 9

FILE CHANGES                             -10

Enter number of the modification desired 1

**** PRESENT TITLE IS P&L CONSTRUCTION

ENTER NEW TITLE ?  P&L_CONSTRUCTION_PROJECT

PC PROJECT MANAGEMENT               8                     USER'S MANUAL

Project: P&L CONSTRUCTION PROJECT                  File: LLP.CPM

Time Period Units: WORKING DAYS   Activities: 48   Start Date: 070183

INPUT MODIFICATION MENU

EXIT MODIFICATION                        - 0

CHANGE TITLE                             - 1

INPUT/ADD ACTIVITIES                     - 2

DELETE ACTIVITIES                        - 3

CHANGE ACTIVITY DATA                     - 4

CHANGE TIME PERIOD UNITS                 - 5

CHANGE START DATE                        - 6

INSPECT INPUT                            - 7

CHECK NODE CONNECTIONS                   - 8

SORT AND FILE INPUT                      - 9

FILE CHANGES                             -10

**** BE SURE TO FILE ANY CHANGES IF YOU WANT THEM ****

/*   This message appears as a reminder to file the

changes you've just made before exiting the

modification menu.  It is not necessary to file

changes after each menu option--only before

returning to the Main Menu.

PC PROJECT MANAGEMENT               9                     USER'S MANUAL

INPUT_OPTION_2_-_INPUT/ADD_ACTIVITIES

Project: P&L CONSTRUCTION PROJECT                  File: LLP.CPM

Time Period Units: WORKING DAYS   Activities: 48   Start Date: 070183

INPUT MODIFICATION MENU

EXIT MODIFICATION                        - 0

CHANGE TITLE                             - 1

INPUT/ADD ACTIVITIES                     - 2

DELETE ACTIVITIES                        - 3

CHANGE ACTIVITY DATA                     - 4

CHANGE TIME PERIOD UNITS                 - 5

CHANGE START DATE                        - 6

INSPECT INPUT                            - 7

CHECK NODE CONNECTIONS                   - 8

SORT AND FILE INPUT                      - 9

FILE CHANGES                             -10

Enter number of the modification desired   2

Project: P&L CONSTRUCTION PROJECT                  File: LLP.CPM

Time Period Units: WORKING DAYS   Activities: 48   Start Date: 070183

SUBCONTRACTOR/COMMENT CODES                **** ACTIVITY 49 ****

1 WILSON  17 MACFORD  33 KRENCHIK  Enter Description

2 JONES   18 MCCALL   34 LEACH     ? ADDITION

3 MILLER  19 TRAMMEL  35 FREEHAN   Enter FROM node ? 180

4 ARCHS   20 WHITE    36 TRESH     Enter TO node ? 190

5 LEMON   21 CABELL   37 WERST     Enter Estimated Time ? 4

6 BUGMAN  22 BROOK    38 LOLICH    Enter finish date (MMDDYY) ? 0

7 SHECK   23 GIBSON   39 BUNNING   Enter percent complete (###) ? 0

8 WILLS   24          40 MCLAIN    Enter Subcontractor/Comment code ? 7

9 MEAD    25 KALINE   41 NORTHRUP  Enter activity cost ($) ? 0

10 KNOUS  26 WILSON   42 STANLEY

11 HOM    27 PARR     43 OYLER     Enter more activities (Y/N) ? N

12 HEDIN  28 MORRIS   44 CASH

13 ROBER  29 BEREN    45 WOCKFUSS

14 MAST   30 WILCOX   46 GRUBB

15 JONEY  31 LOPEZ    47 COBB

16 FURRER 32 BAIR     48 GRENBERG

PC PROJECT MANAGEMENT              10                     USER'S MANUAL

INPUT_OPTION_3_-_DELETE_ACTIVITIES

Project: P&L CONSTRUCTION PROJECT                  File: LLP.CPM

Time Period Units: WORKING DAYS   Activities: 49   Start Date: 070183

INPUT MODIFICATION MENU

EXIT MODIFICATION                        - 0

CHANGE TITLE                             - 1

INPUT/ADD ACTIVITIES                     - 2

DELETE ACTIVITIES                        - 3

CHANGE ACTIVITY DATA                     - 4

CHANGE TIME PERIOD UNITS                 - 5

CHANGE START DATE                        - 6

INSPECT INPUT                            - 7

CHECK NODE CONNECTIONS                   - 8

SORT AND FILE INPUT                      - 9

FILE CHANGES                             -10

**** BE SURE TO FILE ANY CHANGES IF YOU WANT THEM ****

Enter number of the modification desired   3

**** WHEN DELETING, START WITH THE LAST ACTIVITY FIRST

FOR BEST RESULTS ****

**** WHEN CHANGING INPUT, REFER TO THE ACTIVITY POSITION WHICH IS

DISPLAYED IN THE INPUT INSPECTION ROUTINE ****

Inspect the activity file (Y/N/#)

/*   Y     If a "Y" response is given, the activity

file is displayed, beginning with Activity

Position #1.

/*   N     If a "N" response is given, the system asks

"Enter number of activity to change" (input

the Activity Position Number you wish to modify.)

/*   #     Responding with an activity position number will

produce the inspection file, beginning with that

number.

Inspect the activity file (Y/N/#)  40

PC PROJECT MANAGEMENT              11                     USER'S MANUAL

ACT               FROM  TO  ACT  EST   REPORT  % SUB NAME ACT

POS  _DESCRIPTION NODE NODE TIME TIME  FINISH DUN COMMENT COST

40   CURBS & SID   650  960    5    5       0   0 MCCLAIN   $0

41   FINAL CLEAN   960  970    2    2       0   0 NORTHRUP  $0

42   DUMMY         600  620    0    0       0   0 STANLEY   $0

43   ROOF HATCH    890  950    1    1       0   0 OYLER     $0

44   DUMMY         587  590   10   10       0   0 CASH      $0

45   METAL DECK    587  597   25   25       0   0 WOCKFUSS  $0

46   DUMMY         810  955    0    0       0   0 GRUBB     $0

47   DUMMY         595  597    5    5       0   0 COBB      $0

48   TOILET ACC    940  960    2    2       0   0 GRENBERG  $0

49   ADDITION      180  190    4    4       0   0 SHECK     $0

Press ENTER to continue <CR>

Enter position number of the activity to delete - 0 to exit ? 49

Enter position number of the activity to delete - 0 to exit ? 0

PC PROJECT MANAGEMENT              12                     USER'S MANUAL

INPUT_OPTION_4_-_CHANGE_ACTIVITY_DATA

Project: P&L CONSTRUCTION PROJECT                  File: LLP.CPM

Time Period Units: WORKING DAYS   Activities: 48   Start Date: 070183

INPUT MODIFICATION MENU

EXIT MODIFICATION                        - 0

CHANGE TITLE                             - 1

INPUT/ADD ACTIVITIES                     - 2

DELETE ACTIVITIES                        - 3

CHANGE ACTIVITY DATA                     - 4

CHANGE TIME PERIOD UNITS                 - 5

CHANGE START DATE                        - 6

INSPECT INPUT                            - 7

CHECK NODE CONNECTIONS                   - 8

FILE CHANGES                             - 9

**** BE SURE TO FILE ANY CHANGES IF YOU WANT THEM ****

Enter number of the modification desired  _4_

Inspect the activity file (Y/N/#)  20

ACT               FROM  TO  ACT  EST   REPORT  % SUB NAME ACT

POS  _DESCRIPTION NODE NODE TIME TIME  FINISH DUN COMMENT COST

20   POUR S.O.G.   630  790    8    8       0   0 WHITE     $0

21   STAIRCASES    585  590   25   25       0   0 CABELL    $0

22   PLUB. TOP O   630  890   10   10       0   0 BROOK     $0

23   ELEC. PULL    640  760   10   10       0   0 GIBSON    $0

24   ELEC. FIXTU   760  960    5    5       0   0 GENERAL   $0

25   STAIR FILL    597  710   10   10       0   0 KALINE    $0

26   INSULATION    790  800    2    2       0   0 WILSON    $0

27   DRYWALL       800  810   10   10       0   0 PARR      $0

28   CERAMIC TIL   810  850   20   20       0   0 MORRIS    $0

29   PAINT INTER   810  860   10   10       0   0 BEREN     $0

30   DUMMY         860  870    0    0       0   0 WILCOX    $0

31   STAIN DOORS   870  920    5    5       0   0 LOPEZ     $0

32   FINISH HARD   920  960    5    5       0   0 BAIR      $0

33   METAL SIDIN   650  890    2    2       0   0 KRENCHIK  $0

34   ACCESS LADD   950  960    1    1       0   0 LEACH     $0

35   REGISTERS &   955  957    5    5       0   0 FREEHAN   $0

36   BALANCE H.V   957  960    2    2       0   0 TRESH     $0

37   TOILET FIXT   850  910    5    5       0   0 WERST     $0

Press ENTER to continue, or Q to quit <CR>

PC PROJECT MANAGEMENT              13                     USER'S MANUAL

ACT               FROM  TO  ACT  EST   REPORT  % SUB NAME ACT

POS  _DESCRIPTION NODE NODE TIME TIME  FINISH DUN COMMENT COST

38   TOILET PART   910  940    2    2       0   0 LOLICH    $0

39   PAINT STAIR   710  960    3    3       0   0 BUNNING   $0

40   CURBS & SID   650  960    5    5       0   0 MCCLAIN   $0

41   FINAL CLEAN   960  970    2    2       0   0 NORTHRUP  $0

42   DUMMY         600  620    0    0       0   0 STANLEY   $0

43   ROOF HATCH    890  950    1    1       0   0 OYLER     $0

44   DUMMY         587  590   10   10       0   0 CASH      $0

45   METAL DECK    587  597   25   25       0   0 WOCKFUSS  $0

46   DUMMY         810  955    0    0       0   0 GRUBB     $0

47   DUMMY         595  597    5    5       0   0 COBB      $0

48   TOILET ACC    940  960    2    2       0   0 GRENBERG  $0

Press ENTER to continue <CR>

Enter pointer to activity to change    27

DRYWALL                       800 810 10 10 0 0 PARR   0

Change DESC,FROM NODE,TO NODE,TIME,FINDAT,%,SUB CODE,COST,QUIT

Enter (  D ,   FN    ,  TN   ,  T ,  F   ,%,    S   , C , or Q) TN

Enter the new TO node _870_

_____

DRYWALL                       810 870 10 10 0 0 PARR    0

Change DESC,FROM NODE,TO NODE,TIME,FINDAT,%,SUB CODE,COST,QUIT

Enter (  D ,   FN    ,  TN   ,  T ,  F   ,%,    S   , C , or Q) S

Enter subcode number ? 10

DRYWALL                       810 870 10 10 0 0 KNOUS   0

Change More Activities (Y/N/#) N

PC PROJECT MANAGEMENT              14                     USER'S MANUAL

INPUT_OPTION_5_-_CHANGE_TIME_PERIOD_UNITS

Project: P&L CONSTRUCTION PROJECT                  File: LLP.CPM

Time Period Units: WORKING DAYS   Activities: 48   Start Date: 070183

INPUT MODIFICATION MENU

EXIT MODIFICATION                        - 0

CHANGE TITLE                             - 1

INPUT/ADD ACTIVITIES                     - 2

DELETE ACTIVITIES                        - 3

CHANGE ACTIVITY DATA                     - 4

CHANGE TIME PERIOD UNITS                 - 5

CHANGE START DATE                        - 6

INSPECT INPUT                            - 7

CHECK NODE CONNECTIONS                   - 8

SORT AND FILE INPUT                      - 9

FILE CHANGES                             -10

**** BE SURE TO FILE ANY CHANGES IF YOU WANT THEM ****

Enter number of the modification desired  _5_

**** PRESENT TIME UNITS ARE  WORKING DAYS ****

Enter new time units  CALENDAR_DAYS

**** PCPM WILL OMIT HOLIDAYS BUT NOT WEEKENDS ****

PC PROJECT MANAGEMENT              15                     USER'S MANUAL

INPUT_OPTION_6_-_CHANGE_START_DATE

Project: P&L CONSTRUCTION PROJECT                  File: LLP.CPM

Time Period Units: CALENDAR DAYS  Activities: 48   Start Date: 070183

INPUT MODIFICATION MENU

EXIT MODIFICATION                        - 0

CHANGE TITLE                             - 1

INPUT ADD ACTIVITIES                     - 2

DELETE ACTIVITIES                        - 3

CHANGE ACTIVITY DATA                     - 4

CHANGE TIME PERIOD UNITS                 - 5

CHANGE START DATE                        - 6

INSPECT INPUT                            - 7

CHECK NODE CONNECTIONS                   - 8

SORT AND FILE INPUT                      - 9

FILE CHANGES                             -10

**** BE SURE TO FILE ANY CHANGES IF YOU WANT THEM ****

Enter number of the modification desired  _6_

**** PRESENT START DATE IS 070183 ****

Enter new start date in MMDDYY format ? 10483

/*10483 would be January 4, 1983

PC PROJECT MANAGEMENT              16                     USER'S MANUAL

INPUT_OPTION_7_-_INSPECT_INPUT

Project: P&L CONSTRUCTION PROJECT                  File: LLP.CPM

Time Period Units: CALENDAR DAYS  Activities: 48   Start Date: 10483

INPUT MODIFICATION MENU

EXIT MODIFICATION                        - 0

CHANGE TITLE                             - 1

INPUT/ADD ACTIVITIES                     - 2

DELETE ACTIVITIES                        - 3

CHANGE ACTIVITY DATA                     - 4

CHANGE TIME PERIOD UNITS                 - 5

CHANGE START DATE                        - 6

INSPECT INPUT                            - 7

CHECK NODE CONNECTIONS                   - 8

SORT AND FILE INPUT                      - 9

FILE CHANGES                             -10

Enter number of the modification desired 7

PROJECT TITLE : P&L CONSTRUCTION PROJECT

TIME UNITS    : CALENDAR

START DATE    : 010483

Press ENTER to continue, or Q to quit <CR>

ACT               FROM  TO  ACT  EST   REPORT  % SUB NAME ACT

POS  _DESCRIPTION NODE NODE TIME TIME  FINISH DUN COMMENT COST

1   MOBILIZATION  500  510    2    2       0   0 WILSON    $0

2   GRADE & CLEA  510  520    5    5       0   0 JONES     $0

3   REBAR PIERS   520  530    5    5       0   0 MILLER    $0

4   POUR PIERS    530  550    5    5       0   0 ARCHS     $0

5   EXCAVATE FO   550  560    8    8       0   0 LEMON     $0

6   REBAR FOUND   560  570    5    5       0   0 BUGMAN    $0

7   ANCHOR BOLT   570  580    2    2       0   0 SHECK     $0

8   POUR & CURE   580  585    5    5       0   0 WILLIS    $0

9   STRUCTURAL    585  587   10   10       0   0 MEAD      $0

10   DECK FILL C   590  600   15   15       0   0 KNOUS     $0

11   WELD STRUCT   587  595   20   20       0   0 HOM       $0

12   FIRE PROOFI   620  625    5    5       0   0 HEDIN     $0

13   PRECAST PAN   625  650   20   20       0   0 ROBER     $0

14   P.M. FRAMES   600  790    2    2       0   0 MAST      $0

15   WALL FRAMIN   600  790   20   20       0   0 JONEY     $0

16   SHEET METAL   600  955   40   40       0   0 FURRER    $0

17   ELEC. RGH.    620  640   10   10       0   0 MACFORD   $0

18   MAIN ELEC     640  790   10   10       0   0 MCCALL    $0

19   PLUMBING RG   620  630    5    5       0   0 TRAMMEL   $0

Press ENTER to continue, or Q to quit  <CR>

PC PROJECT MANAGEMENT              17                     USER'S MANUAL

ACT               FROM  TO  ACT  EST   REPORT  % SUB NAME ACT

POS  _DESCRIPTION NODE NODE TIME TIME  FINISH DUN COMMENT COST

20   POUR S.O.G.   630  790    8    8       0   0 WHITE     $0

21   STAIRCASES    585  590   25   25       0   0 CABELL    $0

22   PLUB. TOP O   630  890   10   10       0   0 BROOK     $0

23   ELEC. PULL    640  760   10   10       0   0 GIBSON    $0

24   ELEC. FIXTU   760  960    5    5       0   0 GENERAL   $0

25   STAIR FILL    597  710   10   10       0   0 KALINE    $0

26   INSULATION    790  800    2    2       0   0 WILSON    $0

27   DRYWALL       800  870   10   10       0   0 KNOUS     $0

28   CERAMIC TIL   810  850   20   20       0   0 MORRIS    $0

29   PAINT INTER   810  860   10   10       0   0 BEREN     $0

30   DUMMY         860  870    0    0       0   0 WILCOX    $0

31   STAIN DOORS   870  920    5    5       0   0 LOPEZ     $0

32   FINISH HARD   920  960    5    5       0   0 BAIR      $0

33   METAL SIDIN   650  890    2    2       0   0 KRENCHIK  $0

34   ACCESS LADD   950  960    1    1       0   0 LEACH     $0

35   REGISTERS &   955  957    5    5       0   0 FREEHAN   $0

36   BALANCE H.V   957  960    2    2       0   0 TRESH     $0

37   TOILET FIXT   850  910    5    5       0   0 WERST     $0

Press ENTER to continue, or Q to quit <CR>

ACT               FROM  TO  ACT  EST   REPORT  % SUB NAME ACT

POS  _DESCRIPTION NODE NODE TIME TIME  FINISH DUN COMMENT COST

38   TOILET PART   910  940    2    2       0   0 LOLICH    $0

39   PAINT STAIR   710  960    3    3       0   0 BUNNING   $0

40   CURBS & SID   650  960    5    5       0   0 MCCLAIN   $0

41   FINAL CLEAN   960  970    2    2       0   0 NORTHRUP  $0

42   DUMMY         600  620    0    0       0   0 STANLEY   $0

43   ROOF HATCH    890  950    1    1       0   0 OYLER     $0

44   DUMMY         587  590   10   10       0   0 CASH      $0

45   METAL DECK    587  597   25   25       0   0 WOCKFUSS  $0

46   DUMMY         810  955    0    0       0   0 GRUBB     $0

47   DUMMY         595  597    5    5       0   0 COBB      $0

48   TOILET ACC    940  960    2    2       0   0 GRENBERG  $0

Press ENTER to continue <CR>

PC PROJECT MANAGEMENT              18                     USER'S MANUAL

INPUT_OPTION_8_-_CHECK_NODE_CONNECTIONS

Project: P&L CONSTRUCTION PROJECT                  File: LLP.CPM

Time Period Units: CALENDAR DAYS  Activities: 48   Start Date: 10483

INPUT MODIFICATION MENU

EXIT MODIFICATION                        - 0

CHANGE TITLE                             - 1

INPUT/ADD ACTIVITIES                     - 2

DELETE ACTIVITIES                        - 3

CHANGE ACTIVITY DATA                     - 4

CHANGE TIME PERIOD UNITS                 - 5

CHANGE START DATE                        - 6

INSPECT INPUT                            - 7

CHECK NODE CONNECTIONS                   - 8

SORT AND FILE INPUT                      - 9

FILE CHANGES                             -10

**** BE SURE TO FILE ANY CHANGES IF YOU WANT THEM ****

Enter number of the modification desired  _8_

**** QUIET - COMPUTER THINKING - CHECKING NODES ****

**** START NODES O.K. ****

**** END NODES O.K. ****

Press ENTER to continue <CR>

/*   Checking node connections can also be accomplished

using Option 5 of the Main Menu, "PERFORM CRITICAL PATH

ANALYSIS".

PC PROJECT MANAGEMENT              19                     USER'S MANUAL

INPUT_OPTION_9_-_SORT_AND_FILE_INPUT

Project: P&L CONSTRUCTION PROJECT                  File: LLP.CPM

Time Period Units: CALENDAR DAYS  Activities: 48   Start Date: 10483

INPUT MODIFICATION MENU

EXIT MODIFICATION                        - 0

CHANGE TITLE                             - 1

INPUT/ADD ACTIVITES                      - 2

DELETE ACTIVITIES                        - 3

CHANGE ACTIVITY DATA                     - 4

CHANGE TIME PERIOD UNITS                 - 5

CHANGE START DATE                        - 6

INSPECT INPUT                            - 7

CHECK NODE CONNECTIONS                   - 8

SORT AND FILE INPUT                      - 9

FILE CHANGES                             -10

**** BE SURE TO FILE ANY CHANGES IN YOU WANT THEM ****

Enter number of the modification desired 9

**** SORTING 48 ACTIVITIES ******** SORT COMPLETE ****

**** WRITING FILE TO DISK ****

**** FILE LLP.CPM UPDATED ****

**** READING SORTED FILE ****

10  20  30  40  **** INPUT FILE READ ****

Press ENTER to continue <CR>

PC PROJECT MANAGEMENT              20                     USER'S MANUAL

INPUT_OPTION_0_-_EXIT_MODIFICATION

Project: P&L CONSTRUCTION PROJECT                  File: LLP.CPM

Time Period Units: CALENDAR DAYS  Activities: 48   Start Date: 10483

INPUT MODIFICATION MENU

EXIT MODIFICATION                        - 0

CHANGE TITLE                             - 1

INPUT/ADD ACTIVITIES                     - 2

DELETE ACTIVITIES                        - 3

CHANGE ACTIVITY DATA                     - 4

CHANGE TIME PERIOD UNITS                 - 5

CHANGE START DATE                        - 6

INSPECT INPUT                            - 7

CHECK NODE CONNECTIONS                   - 8

SORT AND FILE INPUT                      - 9

FILE CHANGES                             -10

**** BE SURE TO FILE ANY CHANGES IF YOU WANT THEM ****

Enter number of the modification desired  _0_

Last changes were not filed - Are you sure (Y/N) ?  _N_

/*   Before exiting the Modification Menu and returning

to the Main Menu, any changes made must be filed.

If it is desired, the changes can be stored under a

separate file name.

INPUT_OPTION_10_-_FILE_CHANGES

Project: P&L CONSTRUCTION PROJECT                  File: LLP.CPM

Time Period Units: CALENDAR Fa2S  Activities: 48   Start Date: 10483

INPUT MODIFICATION MENU

EXIT MODIFICATION                        - 0

CHANGE TITLE                             - 1

INPUT/ADD ACTIVITES                      - 2

DELETE ACTIVITIES                        - 3

CHANGE ACTIVITY DATA                     - 4

CHANGE TIME PERIOD UNITS                 - 5

CHANGE START DATE                        - 6

INSPECT INPUT                            - 7

CHECK NODE CONNECTIONS                   - 8

SORT AND FILE INPUT                      - 9

FILE CHANGES                             -10

Enter number of the modification desired  10

Use LLP.CPM as filename (Y/N)  ?  _Y_

**** FILE LLP.CPM UPDATED ****

/*   If "N", System asks "Enter new filename".

PC PROJECT MANAGEMENT              21                     USER'S MANUAL

Project: P&L CONSTRUCTION PROJECT                  File: LLP.CPM

Time Period Units: CALENDAR DAYS  Activities: 48   Start Date: 10483

INPUT MODIFICATION MENU

EXIT MODIFICATION                        - 0

CHANGE TITLE                             - 1

INPUT/ADD ACTIVITIES                     - 2

DELETE ACTIVITIES                        - 3

CHANGE ACTIVITY DATA                     - 4

CHANGE TIME PERIOD UNITS                 - 5

CHANGE START DATE                        - 6

INSPECT INPUT                            - 7

CHECK NODE CONNECTIONS                   - 8

SORT AND FILE INPUT                      - 9

FILE CHANGES                             -10

Enter number of the modification desired  _0_

/*   System returns to Main Menu.

PC PROJECT MANAGEMENT              22                     USER'S MANUAL

OPTION_4_-_CREATE/CHANGE_HOLIDAYS

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER  _4_

**** THIS MODULE CREATES AND MANAGES HOLIDAY [.HOL] FILES ****

Enter the name of the base data file ?   LLP

Enter holidays in MM,DD,YY format (0,0,0 if end) ? 2,21,83

Enter holidays in MM,DD,YY format (0,0,0 if end) ? 5,30,83

Enter holidays in MM,DD,YY format (0,0,0 if end) ? 7,3,83

Enter holidays in MM,DD,YY format (0,0,0 if end) ? 9,5,83

Enter holidays in MM,DD,YY format (0,0,0 if end) ? 11,11,83

Enter holidays in MM,DD,YY format (0,0,0 if end) ? 11,24,83

Enter holidays in MM,DD,YY format (0,0,0 if end) ? 0,0,0

**** LIST OF HOLIDAYS FOR THE BASE DATA FILE LLP ****

1  February 21 1983

2  May 30 1983

3  July 3 1983

4  September 5 1983

5  November 11 1983

6  November 24 1983

/*  The holiday file can also be used to store any

date on which no work was done--such as rain

days, or strikes.  Just enter the days as if

they were holidays.

Do you want to change, add, delete or quit (C/A/D/Q)  _C_

Enter number of holiday to change  _3_

Enter new date in MM,DD,YY format  _7,4,83_

PC PROJECT MANAGEMENT              23                     USER'S MANUAL

**** LIST OF HOLIDAYS FOR THE BASE DATA FILE LLP ****

1 February 21 1983

2 May 30 1983

3 July 4 1983

4 September 5 1983

5 November 11 1983

6 November 24 1983

Do you want to change, add, delete or quit (C/A/D/Q)  _D_

ENTER NUMBER OF HOLIDAY TO DELETE  6

**** LIST OF HOLIDAYS FOR THE BASE DATA FILE LLP ****

1 February 21 1983

2 May 30 1983

3 July 4 1983

4 September 5 1983

5 November 11 1983

Do you want to change, add, delete or quit (C/A/D/Q) _Q_

File changes or Quit (F/Q) ? F

**** FILENAME IS LLP.HOL ****

/*  The file is stored under BASEFILE.HOL and the system returns

to Main Menu.

PC PROJECT MANAGEMENT              24                     USER'S MANUAL

OPTION_5_-_PERFORM_CRITICAL_PATH_ANALYSIS

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER  _5_

Enter the name of the input file [.CPM] ?  _LLP_

10  20  30  40  **** INPUT FILE READ ****

**** BYPASSING SORT ROUTINE ****

The Output Filename is LLP.OUT O.K. (Y/N) ? Y

Want to adjust for reported finish times (Y/N) ? Y

/* A "N" ignores the report finish dates entirely.

**** PROJECT LENGTH IS 140 WORKING DAYS ****

**** THIS WILL TAKE 140 SECONDS IN REGULAR BASIC ****

**** END DATE IS MAY2483 ****

**** READING SUB CONTRACTORS ****

**** OUTPUTTING ANALYSIS AND SORT FILE ****

Want to create an updated schedule (Y/N) _Y_

**** CAUTION: YOU MUST CONSOLIDATE UPDATE FILES BEFORE CALLING

NEW OPTIONS ****

**** FINISHED CPM - WRITING CRITICAL PATH LIST TO FILE ****

/*  An update file called LLP.UPD has been created.

/*  The Critical Path Analysis is complete.  System now

returns to Main Menu.

PC PROJECT MANAGEMENT              25                     USER'S MANUAL

OPTION_6_-_PERFORM_CASH_FLOW_ANALYSIS

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER  _6_

/*  CFA calculates the monthly cash outlays for each activity

throughout the project based on the schedule as calculated by

Option 5.  Costs can be calculated based on early or late start

dates.  Activities which have not yet incurred costs can be

excluded.

Enter the name of the input file [.CPM] ? _LLP_

10  20  30  40 **** INPUT FILE READ ****

Want Early or Late Projection (E/L) ?  _E_

10  20  30  40 **** LGS FILE READ ****

**** NOW FIGURING DAYS - WILL TAKE 35 SECONDS IN REGULAR BASIC ****

**** DAYS FIGURED - DISTRIBUTING COSTS AMONG MONTHS ****

Name of output file is LLP.CFA O.K. (Y/N) ? Y

Want to suppress zero-cost activities  (Y/N)  ?_Y_

**** THINKING  FINISHING ****

**** LLP.CFA CREATED ****

/*  When the calculation is complete, the system returns to

Menu.  The sample Cash Flow Analysis, contained in output

file LLP.CFA, is shown in the appendix.

PC PROJECT MANAGEMENT              26                     USER'S MANUAL

OPTION_7_-_PRODUCE_BAR_CHARTS

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER 7

Enter the name of the input file [.CPM] ? LLP

**** INPUT FILE READ ****

10  20  30  40  **** LGS FILE READ ****

**** CALCULATING DAYS ****

Output File will be LLP.BAR O.K. (Y/N) ? Y

Enter width for the chart.  Enter defaults to 90 : <CR>

/*  The width for the barchart depends on the printer

used and the number of days in the schedule.  The

width is divided into the schedule duration.

Example:

Project duration is 160 days.  Entering a "90" will

produce a barchart with activities represented in

1.78 day segments of time.  This same schedule

duration could produce a barchart represented by

2_day segments of time, if 80 is entered instead.

Any number up to 95 is acceptable for barchart width.

Want whole project or Portion (W/P) _P_

/*   For an example of a bar chart portion, see

below.

Will several portions be placed together (Y/N/HELP)  _HELP_

PC PROJECT MANAGEMENT              27                     USER'S MANUAL

If you want to put several portions together, reply

"Y".  PCPM will space activities within each portion so

the activities which extend from one portion to another

will be in alignment when the barcharts are placed side

by side.

Will several portions be placed together (Y/N/Help)  _Y_

Enter beginning date in MMDDYY format  010483

/*  The date entered must be after the start of the

project, before the end of the project, and a

"real" date (for instance, if you are using

working days, the date cannot be a holiday or

weekend).

Enter ending date (MMDDYY) or length in days  140

**** EACH COLUMN WILL REPRESENT 1.56 CALENDAR DAYS ****

*** FORMING BAR CHART ***

Want another Bar Chart from the same run (N/Y)  _N_

PC PROJECT MANAGEMENT              28                     USER'S MANUAL

OPTION_8_-_SORT_OUTPUT

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER   _8_

/*  Output can be requested with data arranged in a variety of

sorts.  The choices are listed in the sort menu.

Enter the name of the input file [.CPM] _LLP_

10  20  30  40  **** INPUT FILE READ ****

CHOICE OF SORTS

NO SORT (RETURN TO MENU)                - 0

FROM NODES                              - 1

TO NODES                                - 2

ESTIMATED DURATIONS                     - 3

ACTUAL DURATIONS                        - 4

EARLY START DATES                       - 5

LATE START DATES                        - 6

EARLY FINISH DATES                      - 7

LATE FINISH DATES                       - 8

FLOAT (CRITICAL PATH)                   - 9

SUBCONTRACTOR CODE/NAME                 - 10

Enter the number of your sort choice ? _5_

**** SORTING 48 ACTIVITIES - TAKES 16 SECONDS IN REGULAR BASIC ****

**** FINISHED SORT - FIGURING DAYS - TAKES 35 SECONDS ****

**** DAYS FIGURED - READING SUBCONTRACTORS ****

**** FILE LLP.SBC READ - 48 SUBCONTRACTORS READ ****

Output Filename is LLP.SRT O.K. (Y/N) ? Y

/*   In the example above, the activities will be sorted in

order of early start dates.

PC PROJECT MANAGEMENT              29                     USER'S MANUAL

/*   The subcontractor name sort option groups all subs with

the same name together on the printout in code, not

alphabetical order.  If you wish each subcontractor

to be listed on a separate printout, use Option 9

of the Main Menu, "EXTRACT OUTPUT BY SUBCONTRACTOR."

CHOICE OF SORTS

NO SORT (RETURN TO MENU)                - 0

FROM NODES                              - 1

TO NODES                                - 2

ESTIMATED DURATIONS                     - 3

ACTUAL DURATIONS                        - 4

EARLY START DATES                       - 5

LATE START DATES                        - 6

EARLY FINISH DATES                      - 7

LATE FINISH DATES                       - 8

FLOAT (CRITICAL PATH)                   - 9

SUBCONTRACTOR CODE/NAME                 - 10

Enter the number of your sort choice ? 0

PC PROJECT MANAGEMENT              30                     USER'S MANUAL

OPTION_9_-_EXTRACT_OUTPUT_BY_SUBCONTRACTOR

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER    _9_

PROGRAM TO EXTRACT SPECIFIC SUBCONTRACTOR PCPM OUTPUT

Enter the name of the input file ? _LLP_

**** INPUT FILE READ ****

Enter subcontractor code (0 to exit) ? 10

Output File is LLP.KNO, O.K. (Y/N) ? Y

/*   The data for each subcontractor selected appears in an

output file named "filename.subname".  (LLP.KNO in this

example.)  Each file contains only activities which are

related to that contractor.

/*   The system returns to Main Menu.

PC PROJECT MANAGEMENT              31                     USER'S MANUAL

OPTION_10_-_CHECK_NODE_NUMBERS

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER _10_

**** THIS MODULE PRINTS THE NODE NUMBERS USED IN A PROJECT ****

/*   This option is useful to avoid duplication of

node numbers.

Enter the name of the input file [.CPM] ? _LLP_

**** INPUT FILE READ ****

**** SORTING NODES ****

**** THE FOLLOWING NODE NUMBERS ARE USED IN: LLP.CPM ****

500 510 520 530 550 560 570 580 585 587 590 597 600 620 625

630 640 650 710 760 790 800 810 850 860 870 910 920 940 950

955 957 960 970 **** CREATING FILE OF NODE NUMBERS ****

**** LLP.NDS CREATED - USE OPTION 14 TO GLOBALLY CHANGE NODES ****

**** CREATING FILE OF NODE NUMBERS - LLP.NDS ****

**** FILE: LLP.NDS CREATED - USE OPTION 14 TO GLOBALLY

CHANGE NODES ****

Press ENTER to continue <CR>

PC PROJECT MANAGEMENT              32                     USER'S MANUAL

OPTION_11_-_GET_PRECEDENCE_OR_SUCCEEDENCE_DISPLAY

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER _11_

/*  This option is used for diagnostic purposes to

determine the cause of errors.

Enter the name of the input file [.CPM] ? _LLP_

10  20  30  40  **** INPUT FILE READ ****

Enter Predecessor or Successor (P/S) P

**** SORTING 48 ACTIVITIES **** FINISHED SORTING ****

**** THE FOLLOWING INDICATES HOW MANY PRECEEDOR S EXIST FOR EACH

ACTIVITY ****

0 1 1 1 1 1 1 1 1 1 1 1 1 2 1 2 1 1 1 1 1 1 1 1 1 1 1 1 1 1 1 1 4 1

1 1 1 1 1 2 1 1 1 1 2 1 7

/*  These numbers may be ignored.  Each number stands for the

number of preceedors (or succeedors) each activity has.

For the actual preceedors, refer to the output file

"BASENAME.PRE".

**** PRECEEDOR DISPLAY CREATED AND EXISTS IN LLP.PRE ****

Press ENTER to continue <CR>

/*  System returns to Main Menu

PC PROJECT MANAGEMENT              33                     USER'S MANUAL

OPTION_12_-_CONVERT_WORKING_DAYS_TO_PROJECT_DAYS

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER _12_

/*   This option creates a calendar of the project's

life.  The start date becomes "Day 1" and each

succeeding day is assigned a succeeding number.

The user can request the Project Day for any

individual day, or he can request a printout of the

calendar for the entire project.

Enter the name of the input file [.CPM] ? _LLP_

**** INPUT FILE READ ****

Enter project length (days) _140_

**** READING HOLIDAY FILE: LLP.HOL ****

**** CALCULATING DAYS - TAKES 60 SECONDS ****

Want a Particular day, Whole printout, or End (P/W/E) _P_

Enter the project day number _31_

DAY 31 IS FEB0483

Want a Particular day, Whole printout, or End (P/W/E) _W_

**** LLP.DAY HAS BEEN CREATED ****

Press ENTER to continue <CR>

/*   System returns to Main Menu.

PC PROJECT MANAGEMENT              34                     USER'S MANUAL

OPTION_13_-_GENERATE_CURRENT_COST_REPORT

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER _13_

/*   This option generates a report of costs expended

to date based on percentage of completion of each

activity.  The output shows total monies spent per

activity.  An example of the output (contained in

BASEFILE.CST) is shown in the appendix.

**** PROGRESS COST REPORT ****

Enter the name of the input file [.CPM] _LLP_

10  20  30  40  **** INPUT FILE READ ****

**** FILE LLP.SBC READ - 48 SUBCONTRACTORS READ ****

Want to suppress Zero-cost activities (Y/N) _Y_

/*   Activities for which no costs have been incurred can

be excluded from the output, if desired.

TOTAL ESTIMATE =         0 AMOUNT EXPENDED =       0

**** LLP.CST HAS BEEN CREATED ****

Press ENTER to continue <CR>

/*   System returns to Main Menu.

PC PROJECT MANAGEMENT              35                     USER'S MANUAL

OPTION_14_-_CHANGE_ALL_NODE_NUMBERS

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER _14_

/*  Option 14 automatically changes node numbers within

a file.  This is useful when project expansion requires

that new activities be added between existing activities

where there is no node space available.  Option 14 can

change the existing nodes in two ways:

1)  By multiplying all the nodes by the same integer factor

2)  An integer number can be selected to be added to all nodes

Either or both methods may be used.

Enter the name of the input file [.CPM] ? _LLP_

20  40  **** INPUT FILE READ ****

**** THIS MODULE ALLOWS YOU TO CHANGE NODES EITHER MATHEMATICALLY

OR BY USING A [.NDS] FILE SET UP BY OPTION 10 OF THE MAIN MENU ****

Change Mathematically, by [.NDS] File, or Quit (M/F/Q) ? M

Enter amount to multiply to all nodes _20_

**** MAXIMUM MULTIPLE IS 1.  TRY AGAIN (ENTER 1 FOR NO CHANGE) ****

/*   The maximum multiple will vary for each project.

Enter amount to multiply to all nodes _1_

Enter amount to add to all nodes _0_

**** FILE LLP.CPM UPDATED ****

Press ENTER to continue <CR>

PC PROJECT MANAGEMENT              36                     USER'S MANUAL

OPTION_15_-_CONSOLIDATENUPDATEMFILE_TO_INPUT_FILE

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER _15_

Enter the name of the input file [.CPM] ? LLP

10  20  30  40  **** INPUT FILE READ ****

File LLP updated - O.K. to write to disk (Y/N) ? Y

10  20  30  40  **** FILE LLP.CPM UPDATED ****

/* the system automatically returns to the main menu.

PC PROJECT MANAGEMENT              37                     USER'S MANUAL

OPTION_0_-_EXIT_PCPM_SYSTEM

MENU OF PCPM PROGRAMS

EXIT PCPM SYSTEM                           -  0

INFORMATION                                -  1

ENTER/CHANGE SUBCONTRACTOR/COMMENT FILE    -  2

ENTER/CHANGE INPUT FILE                    -  3

ENTER/CHANGE HOLIDAYS                      -  4

PERFORM CRITICAL PATH ANALYSIS             -  5

PERFORM CASH FLOW ANALYSIS                 -  6

PRODUCE BAR CHARTS                         -  7

SORT OUTPUT                                -  8

EXTRACT OUTPUT BY SUBCONTRACTOR            -  9

CHECK NODE NUMBERS                         - 10

GET PRECEDENCE OR SUCCEEDENCE DISPLAY      - 11

CONVERT WORKING DAYS TO PROJECT DAYS       - 12

GENERATE CURRENT COST REPORT               - 13

CHANGE ALL NODE NUMBERS                    - 14

CONSOLIDATE UPDATE FILES TO INPUT FILES    - 15

CHOOSE THE ACTION BY ENTERING THE CORRECT INTEGER _0_

EXITING PCPM SYSTEM - GOODBYE FOR NOW

PC PROJECT MANAGEMENT              38                     USER'S MANUAL

III.  IN_CASE_OF_SYSTEM_ERRORS

As many  error  traps  as  possible  have  been included to insure

efficient usage.  However, PCPM does not  check  every  item  each

time in order to keep processing time at a minimum.

If the  syStem  appears to  be "hung up", use the CTRL BREAK keys.

Enter the system again and check for unconnected nodes, or illegal

date usage.  The most common error is made  by  editing  the  data

files outside the PCPM system and leaving out commas or putting in

extra data.   The  simplest  solution is to perform editing within

the PCPM system.

PC PROJECT MANAGEMENT              39                     USER'S MANUAL

IV.  OUTPUT

After exiting the PCPM system, output can be obtained by following

the directions for your printer.

A.  Primary_Output

Primary output is a  list  of  all  activities  including

their estimated duration, actual duration (if completed),

early and  late start times, early and late finish times,

float, actual reported  finish  date,  and  subcontractor

name (or  any  comment)  associated  with  the  activity.

There is also a complete listing  of  all  critical  path

activities following  the  path(s)  from start to finish.

Primary output can be arranged in a variety of  sorts  by

utilizing Option 8.

B.  Cash_Flow_Analysis_Output

This analysis projects monies  to  be  expended  on  each

activity during each month of the project.

C.  Bar_Chart_Output

PCPM outputs  a Gantt type bar chart showing the critical

path, float and activity duration using early start times

for each activity.

D.  Current_Cost_Report

This report shows total costs expended to date  for  each

activity based on percentage of project completion.

E.  Preceeder_or_Succeeder_Display

This   report  shows  the  immediate   interrelationships

between activities - which activity immediately  preceeds

or succeeds  any  other activity as described by its from

and to nodes.

PC PROJECT MANAGEMENT              40                     USER'S MANUAL

V.  APPENDIX

A.  SAMPLE INPUT FORM

-----------------------------------------------------------

FROM   TO   EST   REPORT  %  SUBCONTRACTOR ACT

DESCRIPTION NODE  NODE  TIME  FINISH  DUN  CODE (NAME) COST

-----------------------------------------------------------

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

___________________________________________________________

------------------------------------------------------------

This disk copy provided as a service of

The Public (Software) Library

For a copy of the latest monthly software library newsletter

and a list of the 600+ disks in the library, call or write

The Public (Software) Library

P.O.Box 35705

Houston, TX 77235-5705

(713) 721-6104

Newsletter subscriptions are available for $12 a year.